## Contacts
Developers (Team Orange)
Name | Phone | Email | Skype | Google Hangouts | Github
Scott Bushyhead | 918-521-8314 | bushyhead@gmail.com | bushyhead@gmail.com | bushyhead@gmail.com | NerdAlert58
Ammar Hassan | 918-933-9263 | ammarh@okstate.edu | ammarh@okstate.edu | ammarhz.7j@gmail.com | ammarhz
Srivalli Kanchibotla | 405-780-2321 | srivalli.kanchibotla@okstate.edu | sri.sasthry@gmail.com | sri.sasthry@gmail.com | srivalli93
Tyler Weppler | 316-641-9291 | tyler.weppler@okstate.edu | tweppler44@yahoo.com | nerdboytyler@gmail.com | NerdboyTyler
Hotel Management
Name | Phone | Email

## Tasks
Project | Task | Status | Owner | Helper | Start Date | Expected End Date | Estimated Hours | Completion Date | Comments
HW 4 (Example) | Questions | In Progress | Scott | Sri, Tyler, Ammar | 2016-09-07 | 2016-09-07 | 4 | 2016-09-07 | This is an example of what we can do to keep track of all tasks on the group project. Sep 14- In progress, assignment changed
Github | Create Account and Repo | Completed | Scott |  | 2016-09-07 | 2016-09-14 | 1 | 2016-09-07 | Account: bushyhead@gmail.com Repo: https://github.com/NerdAlert58/CS4153
Github | Create Account | Completed | Sri |  | 2016-09-07 | 2016-09-14 | 1 | 2016-09-07 | Account: srivalli93
Github | Create Account | Completed | Tyler |  | 2016-09-07 | 2016-09-14 | 1 | 2016-09-07 | Account: NerdboyTyler
Github | Create Account | Completed | Ammar |  | 2016-09-07 | 2016-09-14 | 1 | 2016-09-09 | Account: ammarhz
T01_Orange | Complete 1st Team Project | Assigned | Scott | Sri, Tyler, Ammar | 2016-09-07 | 2016-09-27
T01_Orange | Design | In Progress |  |  | 2016-09-13
T01_Orange | Splash Screen | Completed | Scott |  | 2016-09-13 | 2016-09-16 | 2 | 2016-09-18 | Needs review/acceptance by team
T01_Orange | Gestures | Assigned | Tyler |  | 2016-09-13 | 2016-09-16 | 2
T01_Orange | Method: Randomizer | Assigned | Sri |  | 2016-09-13 | 2016-09-16 | 2
T01_Orange | Method: Display | Started |  |  | 2016-09-13 | 2016-09-16
T01_Orange | Level 1 Ideas 3X3
T01_Orange | Level 2 Ideas 4X4
T01_Orange | Level 3 Ideas 5X5
T01_Orange | Testing Level 1
T01_Orange | Testing Level 2
T01_Orange | Testing Level 3